## Schedule-P1
Phase 01 - Prototype V1 From: 23-May-2016 To: 24-June-2016
Function ID | Description | Severity | Start Date | End Date | Actual Start Date | Actual End Date | Assignee | Completion
FID_01 | Soil Moisture measurement | Critical | 2016-05-23 | 2016-05-28 |  |  | Tung Nguyen, Huy Dang | 0%
FID_02 | Temperature measurement | Critical | 2016-05-23 | 2016-05-28 |  |  | Tung Nguyen, Huy Dang | 0%
FID_03 | Light measurement | Critical | 2016-05-29 | 2016-06-10 |  |  | Tung Nguyen, Huy Dang | 0%
FID_04 | Humidity measurement | Critical | 2016-05-29 | 2016-06-10 |  |  | Tung Nguyen, Huy Dang | 0%
FID_05 | Valve and water controlling | Critical | 2016-05-23 | 2016-05-31 |  |  | Huy Dang | 0%
FID_06 | LED controlling | Critical | 2016-05-23 | 2016-05-31 |  |  | Huy Dang | 0%
FID_07 | Remote controlling via Mobile Application (Local Mode) | High | 2016-05-23 | 2016-06-10 |  |  | Phu Quach, Huy Dang | 0%
FID_08 | WIFI development (Local Mode) | High | 2016-05-23 | 2016-06-10 |  |  | Phu Quach, Huy Dang | 0%
FID_09 | Communication between machine & mobile (Local Mode) | High | 2016-06-11 | 2016-06-20 |  |  | Phu Quach, Huy Dang | 0%
FID_10 | Data reporting on demand (Local Mode) | High | 2016-06-11 | 2016-06-20 |  |  | Phu Quach, Huy Dang | 0%
FID_11 | Error Detection/Handling/Reporting | High | 2016-06-11 | 2016-06-20 |  |  | Phu Quach | 0%
[7 empty] | Total completion | 0%